## Sheet1
Section	Task	Belief	26 Aug 3pm	25 Aug 11pm	25 Aug 8pm

Test login and logout
	login works	ok	ok	untested	ok
	logout works	ok	ok	untested	ok
	don't see edit links when not logged in	ok	ok	untested	ok
	do see edit links when logged in	ok	ok	untested	ok
Test delegation
	test delegation box works	ok	ok	untested	ok
	test delegation ok on disk	ok	untested	untested	ok			(need to impl login aliasing to test)
	test partial delegate partially hides	ok	untested	untested	ok
	test delegate autocomplete	unimpl	unimpl	untested	unimpl
	test rescind works	ok	ok	untested	ok
	test rescind ok on disk	ok	untested	untested	ok			(need to impl login aliasing to test)
	test partial delegate hides in dropdown	ok	untested	untested	ok			(need to impl login aliasing to test)
	check delegation and rescind appear in logs	ok	ok	untested	ok
List page
	check main link takes you to view view on list page	broken	broken	untested	broken
	check download spreadsheet link works	ok	ok	untested	ok
	check spreadsheet can be reuploaded and successfully uploads	ok	ok	untested	ok
	check audit status can be updated	ok	ok	untested	ok
Locking
	mock logins to check locks	ok	untested	untested	ok			(need to impl login aliasing to test)
	verify lock stealing	unimpl	untested	untested	unimpl
	verify lock shyness	unimpl	untested	untested	unimpl
spreadsheets
	check spreadsheet is valid CSV and data is correct	ok	ok	untested	ok
	check foot and head are present and correct	ok	ok	untested	ok
	check change to head / foot updates the database	ok	ok	untested	ok			(too much collapsing)
	check change to data rows updates database including calendar and details views	ok	ok	untested	ok
	verify informative failure for time format errors	broken	broken	untested	broken			get “bad lex” exception (or similar)
	verify informative failures for user ID failures	ok	ok	untested	unimpl
	verify failure for wrong upload	broken	broken	untested	broken			(works but not friendly)
	verify informative general format errors	broken	broken	untested	broken			[BUG: somteimtes produces unfeidly error, at other times appears to accept (but doesn't)]
calendar view
	check moving an event works and it's updated in the quick view	ok	ok	ok	broken
	check resizing an event works and it's updated in the quick view	ok	ok	ok	not tested
	check speed is ok	barely	barely	broken	broken
	check titles are good	unimpl	unimpl	unimpl	unimpl
quick edit
	check changing people and places works in dropdown	broken	broken	broken	broken			[BUG: return quickedit is screwed]
	check changing times works in dropdown and that the rectangle moves	ok	ok	ok	broken
	check multiple quickedit changes all change	ok	ok	ok	not tested
	check that time format errors are handled gracefully	unimpl	unimpl	untested	unimpl
	check update details button works	ok	ok	untested	ok
	check dropdown includes good info (inc term)	unimpl	unimpl	untested	unimpl
	check autocomplete works in quick	broken	untested	untested	broken
	verify informative failure for user iD errors	unimpl	untested	untested	unimpl			get “bad lex” exception (or similar) [BUG: not reverted] [BUG: updates lead to screwed selection]
basic
	check update of head and foot works correctly.	ok	ok	untested	ok
	check formatting survives through to view	ok	ok	untested	ok
	check interntationalisation works	ok	ok	untested	ok
	check superfluous paragraph tags get stripped	ok	ok	untested	ok
advanced
	check update is reflected in calendar including time changes	ok	ok	untested	ok
	check pattern compaction is good	ok	ok	untested	ok
	check add event works	ok	ok	untested	ok
	check add group works	ok	ok	untested	ok
	check reordering works	ok	ok	untested	ok
	chect person autocomplete works in advanced	broken	broken	untested	broken
	chect building autocomplete works in advanced	unimpl	unimpl	untested	unimpl